## Sheet1
Sources of Project Cost (not labor)
Period Line item cost (could be hour/day/week/month/etc)
[7 empty] | Month | Month | Month | Month | Month | Month | Month | Month | Month | Month
Phase Name | Project Tasks | Material | Comments | Phase % | Full Cost | Allocation to Phase | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | TOTAL PER TASK
General Conditions | Finalize plans and develop estimate with owner, architect |  |  |  |  | 0 | 1: 0 | 0
| Sign contract and notice to proceed |  |  |  |  | 300 | 1: 300 | 300
| Secure Permits |  |  |  |  | 5000 | 1: 4000; 4: 500; 5: 500 | 5000
0
| Subtotal |  |  |  | 0 | 5300 | 4300 | 0 | 0 | 500 | 500 | 0 | 0 | 0 | 0 | 0 | 5300
Site Work | Clear and grub lot |  |  |  |  | 5000 | 1: 5000 | 5000
| Install temporary power service |  |  |  |  | 4500 | 1: 4500 | 4500
| Install underground utilities |  |  |  |  | 5000 | 1: 5000 | 5000
[6 empty] | 0 | [10 empty] | 0
[6 empty] | 0 | [10 empty] | 0
| Subtotal |  |  |  | 0 | 14500 | 14500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14500
Foundation | Excavate for foundations |  |  |  |  | 3000 | 1: 3000 | 3000
| Form basement walls |  |  |  |  | 2000 | 1: 2000 | 2000
| Place concrete for foundations & basement walls |  |  |  |  | 1500 | 1: 1500 | 1500
| Cure basement walls for 7 days |  |  |  |  | 0 | [10 empty] | 0
| Strip basement wall forms |  |  |  |  | 300 | 1: 300 | 300
| Waterproof/insulate basement walls |  |  |  |  | 500 | 1: 500 | 500
| Perform foundation inspection |  |  |  |  | 540 | 2: 540 | 540
| Backfill foundation |  |  |  |  | 200 | 2: 200 | 200
[6 empty] | 800 | 2: 800 | 800
[6 empty] | 0 | [10 empty] | 0
| Subtotal |  |  |  | 0 | 8840 | 7300 | 1540 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8840
Framing | Install 1st floor joists |  |  |  |  | 1200 | 2: 1200 | 1200
| Lay 1st floor decking |  |  |  |  | 400 | 2: 400 | 400
| Frame 1st floor walls |  |  |  |  | 1200 | 2: 1200 | 1200
| Frame 1st floor corners |  |  |  |  | 400 | 2: 1200 | 1200
| Install 2nd floor joists |  |  |  |  | 1000 | 2: 400 | 400
| Frame 2nd floor decking |  |  |  |  | 400 | 2: 1200 | 1200
| Frame 2nd floor walls |  |  |  |  | 1200 | 3: 1200 | 1200
| Frame 2nd floor corners |  |  |  |  | 400 | 3: 400 | 400
| Complete roof framing |  |  |  |  | 400 | 3: 400 | 400
| Conduct framing inspection |  |  |  |  | 2000 | 3: 2000 | 2000
[6 empty] | 200 | 3: 200 | 200
[6 empty] | 0 | [10 empty] | 0
| Subtotal |  |  |  | 0 | 8800 | 0 | 5600 | 4200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9800
Dry In | Install 1st floor sheathing |  |  |  |  | 3000 | 2: 3000 | 3000
| Install 2nd floor sheathing |  |  |  |  | 3000 | 3: 3000 | 3000
| Install roof decking |  |  |  |  | 1200 | 3: 1200 | 1200
| Install felt, flashing and shingles |  |  |  |  | 1300 | 3: 1300 | 1300
| Hang 1st floor exterior doors |  |  |  |  | 700 | 3: 700 | 700
| Install 1st floor windows |  |  |  |  | 0 | 3: 4000 | 4000
| Install 2nd floor windows |  |  |  |  | 0 | 3: 4000 | 4000
[6 empty] | 0 | [10 empty] | 0
[6 empty] | 0 | [10 empty] | 0
| Subtotal |  |  |  | 0 | 9200 | 0 | 3000 | 14200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17200
Exterior Finishes | Complete exterior brick |  |  |  |  | 1500 | 3: 1500 | 1500
| Complete exterior siding |  |  |  |  | 6000 | 3: 3000; 4: 3000 | 6000
| Paint exterior siding & trim work |  |  |  |  | 600 | 4: 600 | 600
[6 empty] | 0 | [10 empty] | 0
| Subtotal |  |  |  | 0 | 8100 | 0 | 0 | 4500 | 3600 | 0 | 0 | 0 | 0 | 0 | 0 | 8100
Utility Rough-Ins and Complete Concrete | Rough-in plumbing |  |  |  |  | 2000 | 2: 1000; 3: 1000 | 2000
| Conduct rough-in plumbing inspection |  |  |  |  | 200 | 3: 200 | 200
| Place concrete for basement floor |  |  |  |  | 600 | 1: 600 | 600
| Rough-in electrical |  |  |  |  | 2000 | 3: 600 | 600
| Conduct rough-in electrical inspection |  |  |  |  | 200 | 3: 200 | 200
| Rough-in HVAC |  |  |  |  | 1500 | 2: 1000; 3: 500 | 1500
| Conduct rough-in HVAC inspection |  |  |  |  | 300 | 3: 300 | 300
| Rough-in communication - phone, cable, computer, alarm |  |  |  |  | 1000 | 2: 10000 | 10000
[6 empty] | 0 | [10 empty] | 0
[6 empty] | 0 | [10 empty] | 0
| Subtotal |  |  |  | 0 | 7800 | 600 | 12000 | 2800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15400
Interior Finishes | Place wall insulation - 1st floor |  |  |  |  | 800 | 3: 800 | 800
| Place wall insulation - 2nd floor |  |  |  |  | 800 | 4: 800 | 800
| Place ceiling insulation - 2nd floor |  |  |  |  | 600 | 4: 600 | 600
| Conduct insulation inspection |  |  |  |  | 250 | 4: 250 | 250
[6 empty] | 0 | [10 empty] | 0
| Install drywall - 1st floor walls |  |  |  |  | 1200 | 4: 1200 | 1200
| Install drywall - 1st floor overhead |  |  |  |  | 700 | 4: 700 | 700
| Install drywall 2nd floor walls |  |  |  |  | 1300 | 4: 1200 | 1200
| Install drywall 2nd floor overhead |  |  |  |  | 700 | 4: 700 | 700
| Tape and float 1st floor drywall |  |  |  |  | 150 | 4: 150 | 150
| Tape and float 2nd floor drywall |  |  |  |  | 150 | 4: 150 | 150
[6 empty] | 0 | [10 empty] | 0
| Texture all except entry and kitchen - 1st floor |  |  |  |  | 200 | 5: 200 | 200
| Paint all except entry and kitchen - 1st floor |  |  |  |  | 200 | 5: 200 | 200
| Hang wallpaper entry and kitchen - 1st floor |  |  |  |  | 250 | 5: 250 | 250
| Texture all - 2nd floor |  |  |  |  | 200 | 5: 200 | 200
| Paint all - 2nd floor |  |  |  |  | 300 | 5: 300 | 300
| Paint exterior siding & trim work |  |  |  |  | 600 | 5: 600 | 600
[6 empty] | 0 | [10 empty] | 0
| Install 1st floor - kitchen cabinets |  |  |  |  | 8000 | 5: 8000 | 8000
| Install 1st floor - master bath and guest cabinets |  |  |  |  | 2500 | 5: 2500 | 2500
| Install 2nd floor - hall bath and private bath cabinets |  |  |  |  | 1500 | 6: 1500 | 1500
| Install chair rails, crown moldings, trim |  |  |  |  | 800 | 6: 800 | 800
[6 empty] | 600 | 6: 600 | 600
| Complete 1st floor - kitchen plumbing |  |  |  |  | 450 | 6: 450 | 450
| Complete 1st floor - master bath and guest plumbing |  |  |  |  | 1300 | 6: 1300 | 1300
| Complete 2nd floor - hall bath and private bath plumbing |  |  |  |  | 1200 | 6: 1200 | 1200
| Conduct finish plumbing inspection |  |  |  |  | 350 | 6: 350 | 350
[6 empty] | 0 | [10 empty] | 0
| Complete 1st floor circuits to service panel |  |  |  |  | 0 | 7: 1200 | 1200
| Complete 2nd floor circuits to service panel |  |  |  |  | 0 | 7: 1200 | 1200
| Conduct finish electrical inspection |  |  |  |  | 0 | 7: 400 | 400
| Complete communications wiring - phone, cable, computer, alarm |  |  |  |  | 0 | 7: 2000 | 2000
[6 empty] | 0 | [10 empty] | 0
| Complete 1st floor - zone 1 HVAC |  |  |  |  | 1300 | 7: 1300 | 1300
| Complete 2nd floor - zone 2 HVAC |  |  |  |  | 1300 | 7: 1400 | 1400
| Conduct HVAC inspection |  |  |  |  | 400 | 7: 400 | 400
[6 empty] | 0 | [10 empty] | 0
| Tile entry, kitchen and baths |  |  |  |  | 6000 | 7: 6000 | 6000
| Carpet 1st floor |  |  |  |  | 7000 | 7: 7000 | 7000
| Carpet 2nd floor |  |  |  |  | 7000 | 7: 7000 | 7000
| Install appliances |  |  |  |  | 1000 | 7: 1000 | 1000
[6 empty] | 0 | [10 empty] | 0
[6 empty] | 0 | [10 empty] | 0
| Subtotal |  |  |  | 0 | 49100 | 0 | 0 | 800 | 5750 | 12250 | 6200 | 28900 | 0 | 0 | 0 | 53900
Landscaping and Grounds Work | Pour concrete driveway and sidewalks |  |  |  |  | 1500 | 7: 1500 | 1500
| Install backyard fence |  |  |  |  | 5000 | 7: 5000 | 5000
| Sod and complete plantings - front yard |  |  |  |  | 1200 | 7: 1200 | 1200
| Sod and complete plantings - backyard |  |  |  |  | 2000 | 7: 2000 | 2000
[6 empty] | 0 | [10 empty] | 0
[6 empty] | 0 | [10 empty] | 0
| Subtotal |  |  |  | 0 | 9700 | 0 | 0 | 0 | 0 | 0 | 0 | 9700 | 0 | 0 | 0 | 9700
Final Acceptance | Complete final inspection for certificate of occupancy | [5 empty] | 7: 600 | 600
| Cleanup for occupancy | [5 empty] | 7: 1500 | 1500
| Perform final walk-through inspection | [5 empty] | 7: 300 | 300
| Complete punch list items | [5 empty] | 7: 1000 | 1000
0
0
| Subtotal |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3400 | 0 | 0 | 0 | 3400
Subtotals | [5 empty] | 121340 | 26700 | 22140 | 26500 | 9850 | 12750 | 6200 | 42000 | 0 | 0 | 0 | 146140
Material Risk Pool | [16 empty] | 0
Material Risk Contingency | [16 empty] | 0
Material Management Reserve | [16 empty] | 0
Estimated Total Material by Period | [5 empty] | 121340 | 26700 | 22140 | 26500 | 9850 | 12750 | 6200 | 42000 | 0 | 0 | 0 | 146140