## New Design
1 |  | Rates = | 50 | 175 | Internal | External | Internal | External | Internal | External | Internal | External | Internal | External | Internal | External | Internal | External | Internal | External | Internal | External | Internal | External | Internal | External | Internal | External
|  | Deliverable | Duration (months) | Lead | ARCH Hrs. |  | BE DEV Hrs. |  | BSA Hrs. |  | Design/UX/IA Hrs. |  | Legacy ERP DEV Hrs. |  | FE DEV Hrs. |  | PM Hrs. |  | SYS ADMIN Hrs. |  | QA Hrs. |  | Total Hrs. |  | Total # FTE (per Month) |  | Est. Cost
1 | Define | Functional Specifications (x60) | 1 | BSA / Arch | 160 | 0 | 160 | 80 | 160 | 0 | 40 | 0 | 0 | 0 | 40 | 0 | 80 | 0 | 40 | 0 | 120 | 0 | 800 | 80 | 5 | 0.5 | 38250 | 14087.5
2 |  | Technical Specifications | 1 | BSA / Arch | 160 | 0 | 160 | 80 | 160 | 0 | 40 | 0 | 0 | 0 | 40 | 0 | 80 | 0 | 40 | 0 | 120 | 0 | 800 | 80 | 5 | 0.5 | 38250 | 14087.5
3 |  | HTML / Pages Review & Validation | 0.5 | FE Dev / Arch | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 80 | 0 | 10 | 0 | 0 | 0 | 10 | 0 | 120 | 0 | 0.75 | 0 | 5037.5 | 0
4 |  | Finalize Arch Design | 0.75 | Arch | 80 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 40 | 0 | 0 | 0 | 220 | 0 | 1.375 | 0 | 11068.75 | 0
5 | Develop | Dev HTML/CSS/Interactions | 2.5 | FE Dev | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 400 | 0 | 40 | 0 | 0 | 0 | 40 | 0 | 580 | 0 | 3.625 | 0 | 24181.25 | 0
6 |  | Integrate HTML/CSS/Interactions into NetSuite | 1 | FE Dev | 20 | 0 | 80 | 80 | 20 | 0 | 20 | 0 | 0 | 0 | 160 | 0 | 40 | 0 | 40 | 0 | 40 | 0 | 420 | 80 | 2.625 | 0.5 | 20131.25 | 14087.5
7 |  | Setup NetSuite Cloud Environments | 1 | Sys Admin | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 320 | 0 | 0 | 0 | 80 | 0 | 160 | 160 | 10 | 0 | 580 | 160 | 3.625 | 1 | 29181.25 | 28175
8 |  | NS back-end Configuration & Build | 2 | Sys Admin | 10 | 0 | 160 | 320 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 20 | 0 | 220 | 320 | 1.375 | 2 | 10068.75 | 56350
9 |  | Dev 3rd Party Solutions (tax, add ver., pay etc.) | 2 | BE Dev | 0 | 0 | 0 | 320 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 0 | 0 | 80 | 0 | 320 | 320 | 2 | 2 | 16100 | 56350
10 |  | Configure 3rd Party Solutions (tax etc.) | 1 | Sys Admin | 0 | 0 | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 0 | 160 | 0 | 20 | 0 | 340 | 0 | 2.125 | 0 | 17106.25 | 0
11 |  | Develop Integrations & Legacy ERP Solutions | 2 | BE Dev | 0 | 0 | 160 | 40 | 0 | 0 | 0 | 0 | 240 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 410 | 40 | 2.5625 | 0.25 | 20628.125 | 7043.75
12 | QA | Quality Assurance | 2 | QA | 40 | 0 | 80 | 80 | 160 | 0 | 40 | 0 | 40 | 0 | 80 | 0 | 160 | 0 | 80 | 0 | 640 | 160 | 1320 | 240 | 8.25 | 1.5 | 64412.5 | 42262.5
13 |  | End-to-End Testing | 1 | QA | 20 | 0 | 40 | 40 | 80 | 0 | 20 | 0 | 20 | 0 | 40 | 0 | 160 | 0 | 40 | 0 | 320 | 80 | 740 | 120 | 4.625 | 0.75 | 36231.25 | 21131.25
14 |  | Performance Optimization | 1 | Arch | 20 | 0 | 40 | 40 | 80 | 0 | 20 | 0 | 20 | 0 | 40 | 0 | 160 | 0 | 40 | 0 | 320 | 80 | 740 | 120 | 4.625 | 0.75 | 36231.25 | 21131.25
15 |  | User Acceptance Testing (UAT) | 1 | QA | 20 | 0 | 40 | 40 | 80 | 0 | 20 | 0 | 20 | 0 | 40 | 0 | 160 | 0 | 40 | 0 | 320 | 80 | 740 | 120 | 4.625 | 0.75 | 36231.25 | 21131.25
16 | Deploy | Deployment Prep & Readiness | 0.5 | Sys Admin | 20 | 0 | 40 | 40 | 80 | 0 | 20 | 0 | 20 | 0 | 40 | 0 | 160 | 0 | 40 | 0 | 320 | 80 | 740 | 120 | 4.625 | 0.75 | 36231.25 | 21131.25
17 |  | Deploy RVCA eCom | 0 | All | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 10 | 0 | 20 | 0 | 20 | 0 | 20 | 0 | 120 | 0 | 0.75 | 0 | 5537.5 | 0
|  |  | 20.25 |  | 560 | 0 | 1140 | 1160 | 990 | 0 | 370 | 0 | 690 | 0 | 980 | 0 | 1340 | 0 | 740 | 160 | 2400 | 480 | 9210 | 1800 |  |  | 444878.125 | 316968.75
[27 empty] | Total Cost | 761846.875
Copy BBG Design
|  | Duration by Phase (by Month) |  | Hrs | Hrs |  | <--5 month duration
1 |  | Define & Design | 2 | 2100 | 119
3 |  | Build | 4 | 3790 | 1475
4 |  | QA | 3 | 4140 | 3125
5 |  | Deploy | 0.25 | 980 | 560
|  | Total Duration | 9.25 | 11010 | 5279
Assumptions
1 |  | Teams are dedicated and not working on existing H4 or other NetSuite work
2 |  | Assumes very little changes compared to existing Designs & built BBG functionality
3 |  | Estimate excludes Travel cost.
4 |  | Addl. Training may be required.
5 |  | Detailed bottom-up estimate required to validate current estimates
6
7
8
9