## Sheet1
*Note: Need to determine where this material is needed these phases are from WBS solution phasing
Bill of Materials
Project Phase* | Type of Work | Source of Labor | Material (no labor) | Comments | Phase total
| Appliances | Appliances | 7500 |  | 7000 | 500
| Brick facing | Masonry |  | See siding |  | 0
| Carpete, pad. Real hardwood floor for 1st floor, except laundry, master bath is about $8,000 which includes install. Just then the carpet for upstairs and stairways is about $1,000 for both material and labor. | Flooring | 2000 | Charge is usaully fixed price. Bundled for all flooring for home and labor $9,000 add 1/3 for improved grade and material (such as stone vs. porcelain) | 2000 | 0
| Concrete |  | 10000 |  | 10000 | 0
| Deck, if homeowner does, then materials covers standard (12' x 12') | Homeowner | 5000 | If footings and ledger board are included early, then cost is reduced for deck later to about $2,000 (by owner and friend)
| Dimension lumber, nails, trusses, sill sealer, sheething | Framing | 47200 |  | 47000 | 200
| Doors (exterior doors and garage) | Framing | 5000 | Garage doors done by garage guy, usually in door cost | 3000
| erosion controls included in cost of excavation | Excav |  | Moving, finish grading, backfill included
| Excavation, foundations, etc |  | 14000 | If footings early for deck, cost is bumped by $150 | 14000 | 0
| Finish electrical--fixtures, plate |  | 1550 |  | 1550 | 0
| Finish plumbing--sinks, toilets, faucets, shower base |  | 5200 |  | 5190 | 10
| Hanging, taping and texturing | Drywall | 2500 | Labor Charge is usually fixed price not included in material cost and includes taper, hanger and texturer | 2500 | 0
| Insulation, bat, blown, poly barrier, tape |  | 2200 |  | 2200 | 0
| Molding and trim + interior doors + cabinets | Finishing | 25000 | See windows above | 25000 | 0
| Paint inside and out | Painter | 800 | two coats | 800 | 0
| Permits |  | 12000 | Varies by jurisdiction | 12000 | 0
| Roofing, felt, flashing, nails, water shield , drip edge | Framing | 3400 |  | 3400 | 0
| Rough in electric--wiring and outlets, box | Electrician | 1750 |  | 1750 | 0
| Rough Plumbing, water/sewer pipe | Plumber | 3500 |  | 3500 | 0
| siding, tyvek, brick facing | Siding guy | 7900 |  | 7900 | 0
| Sod, shrubs homeowner does, then his/her cost is about $1,200 cost for materials | Landscaper | 2400 | What about a sprinkler system now? Package price would be about $2,000. Post construction install would be about 3x the cost. | 2400 | 0
| Tile, grout, morter, cement board, price drops if hard woods on 1st floor to $1,000 + labor at about $2,000 for the tile required | Flooring | 2400 | Charge is usaully fixed price | 2400 | 0
| Windows | Framing | 12000 | 27windows, no labor | 12000 | 0
Material Total |  |  | 173300 |  | 165590