## WBS
*Note that the project sequence number is not the same as the excel sheet row number
Project Seq. #* | Task Name | Duration | Start | Start After | Finish Before | Finish Date
1 | Single Family House - Architect Design | 20 days | Mon 1/6/14
2 | Start Project Milestone | 0 days | Mon 1/6/14 | Project start | 4
3 | General Conditions | 20 days | Mon 1/6/14 | NA Calculated | NA Calculated
4 | Finalize plans and develop estimate with owner, architect | 20 days | Mon 1/6/14 | 2 | 5
5 | Sign contract and notice to proceed | 1 day | Mon 1/6/14 | 4 | 7-12
6 | Apply for Permits | 10 days | Mon 1/6/14
7 | Secure foundation permit | 10 days | Mon 1/6/14 | 5 | 14
8 | Secure framing permit | 10 days | Mon 1/6/14 | 5 | 14
9 | Secure electrical permit | 10 days | Mon 1/6/14 | 5 | 14
10 | Secure plumbing permit | 10 days | Mon 1/6/14 | 5 | 14
11 | Secure HVAC permit | 10 days | Mon 1/6/14 | 5 | 14
12 | Secure miscellaneous permits | 10 days | Mon 1/6/14 | 5 | 14
13 | Site Work | 1 day | Mon 1/6/14 | NA Calculated | NA Calculated
14 | Clear and grub lot | 1 day | Mon 1/6/14 | 7-11 | 15
15 | Install temporary power service | 1 day | Mon 1/6/14 | 14 | 16
16 | Install underground utilities | 1 day | Mon 1/6/14 | 15 | 18
17 | Foundation | 13 days | Mon 1/6/14 | NA Calculated | NA Calculated
18 | Excavate for foundations | 3 days | Mon 1/6/14
19 | Form basement walls | 13 days | Mon 1/6/14
20 | Place concrete for foundations & basement walls | 12 days | Mon 1/6/14
21 | Cure basement walls for 7 days | 7 days | Mon 1/6/14
22 | Strip basement wall forms | 2 days | Mon 1/6/14
23 | Waterproof/insulate basement walls | 2 days | Mon 1/6/14
24 | Perform foundation inspection | 1 day | Mon 1/6/14
25 | Backfill foundation | 2 days | Mon 1/6/14
26 | Framing | 4 days | Mon 1/6/14
27 | Install 1st floor joists | 2 days | Mon 1/6/14
28 | Lay 1st floor decking | 2 days | Mon 1/6/14
29 | Frame 1st floor walls | 4 days | Mon 1/6/14
30 | Frame 1st floor corners | 1 day | Mon 1/6/14
31 | Install 2nd floor joists | 2 days | Mon 1/6/14
32 | Frame 2nd floor decking | 2 days | Mon 1/6/14
33 | Frame 2nd floor walls | 3 days | Mon 1/6/14
34 | Frame 2nd floor corners | 2 days | Mon 1/6/14
35 | Complete roof framing | 3 days | Mon 1/6/14
36 | Conduct framing inspection | 1 day | Mon 1/6/14
37 | Dry In | 3 days | Mon 1/6/14
38 | Install 1st floor sheathing | 3 days | Mon 1/6/14
39 | Install 2nd floor sheathing | 3 days | Mon 1/6/14
40 | Install roof decking | 3 days | Mon 1/6/14
41 | Install felt, flashing and shingles | 3 days | Mon 1/6/14
42 | Hang 1st floor exterior doors | 1 day | Mon 1/6/14
43 | Install 1st floor windows | 3 days | Mon 1/6/14
44 | Install 2nd floor windows | 3 days | Mon 1/6/14
45 | Exterior Finishes | 16 days | Mon 1/6/14
46 | Complete exterior brick | 16 days | Mon 1/6/14
47 | Complete exterior siding | 3 days | Mon 1/6/14
48 | Utility Rough-B97Ins and Complete Concrete | 11 days | Mon 1/6/14
49 | Rough-in plumbing | 5 days | Mon 1/6/14
50 | Conduct rough-in plumbing inspection | 1 day | Mon 1/6/14
51 | Place concrete for basement floor | 11 days | Mon 1/6/14
52 | Rough-in electrical | 5 days | Mon 1/6/14
53 | Conduct rough-in electrical inspection | 1 day | Mon 1/6/14
54 | Rough-in HVAC | 3 days | Mon 1/6/14
55 | Conduct rough-in HVAC inspection | 1 day | Mon 1/6/14
56 | Rough-in communication - phone, cable, computer, alarm | 2 days | Mon 1/6/14
57 | Interior Finishes | 4 days | Mon 1/6/14
58 | Insulation | 1 day | Mon 1/6/14
59 | Place wall insulation - 1st floor | 1 day | Mon 1/6/14
60 | Place wall insulation - 2nd floor | 1 day | Mon 1/6/14
61 | Place ceiling insulation - 2nd floor | 1 day | Mon 1/6/14
62 | Conduct insulation inspection | 1 day | Mon 1/6/14
63 | Drywall | 2 days | Mon 1/6/14
64 | Install drywall - 1st floor walls | 2 days | Mon 1/6/14
65 | Install drywall - 1st floor overhead | 2 days | Mon 1/6/14
66 | Install drywall 2nd floor walls | 2 days | Mon 1/6/14
67 | Install drywall 2nd floor overhead | 2 days | Mon 1/6/14
68 | Tape and float 1st floor drywall | 1 day | Mon 1/6/14
69 | Tape and float 2nd floor drywall | 1 day | Mon 1/6/14
70 | Paint and Wallpaper | 4 days | Mon 1/6/14
71 | Texture all except entry and kitchen - 1st floor | 1 day | Mon 1/6/14
72 | Paint all except entry and kitchen - 1st floor | 1 day | Mon 1/6/14
73 | Hang wallpaper entry and kitchen - 1st floor | 1 day | Mon 1/6/14
74 | Texture all - 2nd floor | 1 day | Mon 1/6/14
75 | Paint all - 2nd floor | 1 day | Mon 1/6/14
76 | Paint exterior siding & trim work | 4 days | Mon 1/6/14
77 | Cabinets | 2 days | Mon 1/6/14
78 | Install 1st floor - kitchen cabinets | 2 days | Mon 1/6/14
79 | Install 1st floor - master bath and guest cabinets | 1 day | Mon 1/6/14
80 | Install 2nd floor - hall bath and private bath cabinets | 1 day | Mon 1/6/14
81 | Install chair rails, crown moldings, trim | 2 days | Mon 1/6/14
82 | Finish Plumbing | 2 days | Mon 1/6/14
83 | Complete 1st floor - kitchen plumbing | 1 day | Mon 1/6/14
84 | Complete 1st floor - master bath and guest plumbing | 2 days | Mon 1/6/14
85 | Complete 2nd floor - hall bath and private bath plumbing | 2 days | Mon 1/6/14
86 | Conduct finish plumbing inspection | 1 day | Mon 1/6/14
87 | Finish Electrical | 2 days | Mon 1/6/14
88 | Complete 1st floor circuits to service panel | 1 day | Mon 1/6/14
89 | Complete 2nd floor circuits to service panel | 1 day | Mon 1/6/14
90 | Conduct finish electrical inspection | 1 day | Mon 1/6/14
91 | Complete communications wiring - phone, cable, computer, alarm | 2 days | Mon 1/6/14
92 | Finish HVAC | 1 day | Mon 1/6/14
93 | Complete 1st floor - zone 1 HVAC | 1 day | Mon 1/6/14
94 | Complete 2nd floor - zone 2 HVAC | 1 day | Mon 1/6/14
95 | Conduct HVAC inspection | 1 day | Mon 1/6/14
96 | Carpet, Tile and Appliances | 3 days | Mon 1/6/14
97 | Tile entry, kitchen and baths | 3 days | Mon 1/6/14
98 | Carpet 1st floor | 2 days | Mon 1/6/14
99 | Carpet 2nd floor | 2 days | Mon 1/6/14
100 | Install appliances | 1 day | Mon 1/6/14
101 | Landscaping and Grounds Work | 2 days | Mon 1/6/14
102 | Pour concrete driveway and sidewalks | 2 days | Mon 1/6/14
103 | Install backyard fence | 2 days | Mon 1/6/14
104 | Sod and complete plantings - front yard | 2 days | Mon 1/6/14
105 | Sod and complete plantings - backyard | 1 day | Mon 1/6/14
106 | Final Acceptance | 5 days | Mon 1/6/14
107 | Complete final inspection for certificate of occupancy | 1 day | Mon 1/6/14
108 | Cleanup for occupancy | 1 day | Mon 1/6/14
109 | Perform final walk-through inspection | 1 day | Mon 1/6/14
110 | Complete punch list items | 5 days | Mon 1/6/14
111 | End Project Milestone | 0 days | Mon 1/6/14