## WBS
Task Name | Duration | Start | Finish | Predecessors | Successors | Resource Names
Single Family House - Architect Design | 162 days | Mon 1/6/14 | Tue 8/19/14
Start Project Milestone | 0 days | Mon 1/6/14 | Mon 1/6/14 |  | 4
General Conditions | 31 days | Mon 1/6/14 | Mon 2/17/14
Finalize plans and develop estimate with owner, architect | 20 days | Mon 1/6/14 | Fri 1/31/14 | 2 | 5
Sign contract and notice to proceed | 1 day | Mon 2/3/14 | Mon 2/3/14 | 4 | 7,8,9,10,11,12
Apply for Permits | 10 days | Tue 2/4/14 | Mon 2/17/14
Secure foundation permit | 10 days | Tue 2/4/14 | Mon 2/17/14 | 5 | 14
Secure framing permit | 10 days | Tue 2/4/14 | Mon 2/17/14 | 5 | 14
Secure electrical permit | 10 days | Tue 2/4/14 | Mon 2/17/14 | 5 | 14
Secure plumbing permit | 10 days | Tue 2/4/14 | Mon 2/17/14 | 5 | 14
Secure HVAC permit | 10 days | Tue 2/4/14 | Mon 2/17/14 | 5 | 14
Secure miscellaneous permits | 10 days | Tue 2/4/14 | Mon 2/17/14 | 5 | 14
Site Work | 3 days | Tue 2/18/14 | Thu 2/20/14
Clear and grub lot | 1 day | Tue 2/18/14 | Tue 2/18/14 | 7,8,9,10,12,11 | 15
Install temporary power service | 1 day | Wed 2/19/14 | Wed 2/19/14 | 14 | 16
Install underground utilities | 1 day | Thu 2/20/14 | Thu 2/20/14 | 15 | 18
Foundation | 42 days | Fri 2/21/14 | Mon 4/21/14
Excavate for foundations | 3 days | Fri 2/21/14 | Tue 2/25/14 | 16 | 19,24
Form basement walls | 13 days | Wed 2/26/14 | Fri 3/14/14 | 18 | 20
Place concrete for foundations & basement walls | 12 days | Mon 3/17/14 | Tue 4/1/14 | 19 | 21
Cure basement walls for 7 days | 7 days | Wed 4/2/14 | Thu 4/10/14 | 20 | 22
Strip basement wall forms | 2 days | Fri 4/11/14 | Mon 4/14/14 | 21 | 23
Waterproof/insulate basement walls | 2 days | Tue 4/15/14 | Wed 4/16/14 | 22 | 24
Perform foundation inspection | 1 day | Thu 4/17/14 | Thu 4/17/14 | 23,18 | 25
Backfill foundation | 2 days | Fri 4/18/14 | Mon 4/21/14 | 24 | 27
Framing | 22 days | Tue 4/22/14 | Wed 5/21/14
Install 1st floor joists | 2 days | Tue 4/22/14 | Wed 4/23/14 | 25 | 28
Lay 1st floor decking | 2 days | Thu 4/24/14 | Fri 4/25/14 | 27 | 29
Frame 1st floor walls | 4 days | Mon 4/28/14 | Thu 5/1/14 | 28 | 30
Frame 1st floor corners | 1 day | Fri 5/2/14 | Fri 5/2/14 | 29 | 31
Install 2nd floor joists | 2 days | Mon 5/5/14 | Tue 5/6/14 | 30 | 32
Frame 2nd floor decking | 2 days | Wed 5/7/14 | Thu 5/8/14 | 31 | 33
Frame 2nd floor walls | 3 days | Fri 5/9/14 | Tue 5/13/14 | 32 | 34
Frame 2nd floor corners | 2 days | Wed 5/14/14 | Thu 5/15/14 | 33 | 35
Complete roof framing | 3 days | Fri 5/16/14 | Tue 5/20/14 | 34 | 36,40
Conduct framing inspection | 1 day | Wed 5/21/14 | Wed 5/21/14 | 35 | 38
Dry In | 22 days | Wed 5/21/14 | Thu 6/19/14
Install 1st floor sheathing | 3 days | Thu 5/22/14 | Mon 5/26/14 | 36 | 39,59
Install 2nd floor sheathing | 3 days | Tue 5/27/14 | Thu 5/29/14 | 38 | 49,52,59
Install roof decking | 3 days | Wed 5/21/14 | Fri 5/23/14 | 35 | 49,52,56
Install felt, flashing and shingles | 3 days | Fri 6/6/14 | Tue 6/10/14 | 49 | 42
Hang 1st floor exterior doors | 1 day | Wed 6/11/14 | Wed 6/11/14 | 41 | 43
Install 1st floor windows | 3 days | Thu 6/12/14 | Mon 6/16/14 | 42 | 44
Install 2nd floor windows | 3 days | Tue 6/17/14 | Thu 6/19/14 | 43 | 46,59
Exterior Finishes | 19 days | Fri 6/20/14 | Wed 7/16/14
Complete exterior brick | 16 days | Fri 6/20/14 | Fri 7/11/14 | 44 | 47
Complete exterior siding | 3 days | Mon 7/14/14 | Wed 7/16/14 | 46 | 76
Utility Rough-B97Ins and Complete Concrete | 21 days | Mon 5/26/14 | Mon 6/23/14
Rough-in plumbing | 5 days | Fri 5/30/14 | Thu 6/5/14 | 40,39 | 41,50
Conduct rough-in plumbing inspection | 1 day | Fri 6/6/14 | Fri 6/6/14 | 49 | 51,83
Place concrete for basement floor | 11 days | Mon 6/9/14 | Mon 6/23/14 | 50 | 107
Rough-in electrical | 5 days | Fri 5/30/14 | Thu 6/5/14 | 40,39 | 53,59
Conduct rough-in electrical inspection | 1 day | Fri 6/6/14 | Fri 6/6/14 | 52 | 54,88
Rough-in HVAC | 3 days | Mon 6/9/14 | Wed 6/11/14 | 53 | 55,59
Conduct rough-in HVAC inspection | 1 day | Thu 6/12/14 | Thu 6/12/14 | 54 | 93
Rough-in communication - phone, cable, computer, alarm | 2 days | Mon 5/26/14 | Tue 5/27/14 | 40 | 59
Interior Finishes | 30 days | Fri 6/20/14 | Thu 7/31/14
Insulation | 11 days | Fri 6/20/14 | Fri 7/4/14
Place wall insulation - 1st floor | 1 day | Fri 6/20/14 | Fri 6/20/14 | 38,44,56,54,52,39 | 60,64
Place wall insulation - 2nd floor | 1 day | Mon 6/23/14 | Mon 6/23/14 | 59 | 61,66
Place ceiling insulation - 2nd floor | 1 day | Thu 7/3/14 | Thu 7/3/14 | 67,60 | 62
Conduct insulation inspection | 1 day | Fri 7/4/14 | Fri 7/4/14 | 61 | 107
Drywall | 9 days | Mon 6/23/14 | Thu 7/3/14
Install drywall - 1st floor walls | 2 days | Mon 6/23/14 | Tue 6/24/14 | 59 | 65
Install drywall - 1st floor overhead | 2 days | Wed 6/25/14 | Thu 6/26/14 | 64 | 66,68
Install drywall 2nd floor walls | 2 days | Fri 6/27/14 | Mon 6/30/14 | 65,60 | 67
Install drywall 2nd floor overhead | 2 days | Tue 7/1/14 | Wed 7/2/14 | 66 | 61,69
Tape and float 1st floor drywall | 1 day | Fri 6/27/14 | Fri 6/27/14 | 65 | 69,71
Tape and float 2nd floor drywall | 1 day | Thu 7/3/14 | Thu 7/3/14 | 67,68
Paint and Wallpaper | 17 days | Mon 6/30/14 | Tue 7/22/14
Texture all except entry and kitchen - 1st floor | 1 day | Mon 6/30/14 | Mon 6/30/14 | 68 | 72,74
Paint all except entry and kitchen - 1st floor | 1 day | Tue 7/1/14 | Tue 7/1/14 | 71 | 73
Hang wallpaper entry and kitchen - 1st floor | 1 day | Wed 7/2/14 | Wed 7/2/14 | 72 | 78
Texture all - 2nd floor | 1 day | Tue 7/1/14 | Tue 7/1/14 | 71 | 75
Paint all - 2nd floor | 1 day | Wed 7/2/14 | Wed 7/2/14 | 74
Paint exterior siding & trim work | 4 days | Thu 7/17/14 | Tue 7/22/14 | 47 | 102
Cabinets | 6 days | Thu 7/3/14 | Thu 7/10/14
Install 1st floor - kitchen cabinets | 2 days | Thu 7/3/14 | Fri 7/4/14 | 73 | 79,83
Install 1st floor - master bath and guest cabinets | 1 day | Mon 7/7/14 | Mon 7/7/14 | 78 | 80,84
Install 2nd floor - hall bath and private bath cabinets | 1 day | Tue 7/8/14 | Tue 7/8/14 | 79 | 81,85
Install chair rails, crown moldings, trim | 2 days | Wed 7/9/14 | Thu 7/10/14 | 80 | 107
Finish Plumbing | 6 days | Mon 7/7/14 | Mon 7/14/14
Complete 1st floor - kitchen plumbing | 1 day | Mon 7/7/14 | Mon 7/7/14 | 78,50 | 84
Complete 1st floor - master bath and guest plumbing | 2 days | Tue 7/8/14 | Wed 7/9/14 | 83,79 | 85
Complete 2nd floor - hall bath and private bath plumbing | 2 days | Thu 7/10/14 | Fri 7/11/14 | 84,80 | 86,88
Conduct finish plumbing inspection | 1 day | Mon 7/14/14 | Mon 7/14/14 | 85 | 91107
Finish Electrical | 3 days | Mon 7/14/14 | Wed 7/16/14
Complete 1st floor circuits to service panel | 1 day | Mon 7/14/14 | Mon 7/14/14 | 85,53 | 89
Complete 2nd floor circuits to service panel | 1 day | Tue 7/15/14 | Tue 7/15/14 | 88 | 90
Conduct finish electrical inspection | 1 day | Wed 7/16/14 | Wed 7/16/14 | 89 | 97107
Complete communications wiring - phone, cable, computer, alarm | 2 days | Tue 7/15/14 | Wed 7/16/14 | 86 | 93
Finish HVAC | 3 days | Thu 7/17/14 | Mon 7/21/14
Complete 1st floor - zone 1 HVAC | 1 day | Thu 7/17/14 | Thu 7/17/14 | 91,55 | 94
Complete 2nd floor - zone 2 HVAC | 1 day | Fri 7/18/14 | Fri 7/18/14 | 93 | 95
Conduct HVAC inspection | 1 day | Mon 7/21/14 | Mon 7/21/14 | 94 | 97107
Carpet, Tile and Appliances | 8 days | Tue 7/22/14 | Thu 7/31/14
Tile entry, kitchen and baths | 3 days | Tue 7/22/14 | Thu 7/24/14 | 90,95 | 98
Carpet 1st floor | 2 days | Fri 7/25/14 | Mon 7/28/14 | 97 | 99
Carpet 2nd floor | 2 days | Tue 7/29/14 | Wed 7/30/14 | 98 | 100
Install appliances | 1 day | Thu 7/31/14 | Thu 7/31/14 | 99 | 103108
Landscaping and Grounds Work | 12 days | Wed 7/23/14 | Thu 8/7/14
Pour concrete driveway and sidewalks | 2 days | Wed 7/23/14 | Thu 7/24/14 | 76 | 103
Install backyard fence | 2 days | Fri 8/1/14 | Mon 8/4/14 | 100102 | 104
Sod and complete plantings - front yard | 2 days | Tue 8/5/14 | Wed 8/6/14 | 103 | 105
Sod and complete plantings - backyard | 1 day | Thu 8/7/14 | Thu 8/7/14 | 104 | 107
Final Acceptance | 8 days | Fri 8/8/14 | Tue 8/19/14
Complete final inspection for certificate of occupancy | 1 day | Fri 8/8/14 | Fri 8/8/14 | 105,95,90,86,62,81,51 | 108
Cleanup for occupancy | 1 day | Mon 8/11/14 | Mon 8/11/14 | 100107 | 109
Perform final walk-through inspection | 1 day | Tue 8/12/14 | Tue 8/12/14 | 108 | 110
Complete punch list items | 5 days | Wed 8/13/14 | Tue 8/19/14 | 109 | 111
End Project Milestone | 0 days | Tue 8/19/14 | Tue 8/19/14 | 110

## Labor Resources
Resource Name | Rate | Estimated hours | Estimated start | Estimated End
Appliance contractor | 0
Architect | 60
Concrete contractor | 65
Drywall contractor | 58
Electric company | 0
Electric contractor | 45
Fencing contractor | 55
Finish carpentry contractor | 50
Flooring contractor | 76
Framing contractor | 40
General contractor | 70
Heating and AC contractor | 80
Inspector | 0
Insulation contractor | 90
Landscape contractor | 40
Maid service | 50
Masonry contractor | 80
Mortgage lender | 0
Owner | 0
Painting contractor | 47
Plumbing contractor | 45
Roofing contractor | 50
Siding conractor | 42
Site excavation contractor | 150