## MS Practice Exercise
Task Name | Duration | Start | Finish | Predecessors | Work | Cost | Resource Initials
RFP Solicitation Process | 24.33 days | Mon 1/6/14 | Mon 2/10/14 |  | 511 hrs | 27760
RFP Solicitation Process begins | 0 days | Mon 1/6/14 | Mon 1/6/14 |  | 0 hrs | 0
RFP Creation | 19.44 days | Mon 1/6/14 | Mon 2/3/14 |  | 423 hrs | 21420
RFP Creation Begins | 0 days | Mon 1/6/14 | Mon 1/6/14 | 2 | 0 hrs | 0
Document Software requirements | 8 days | Mon 1/6/14 | Thu 1/16/14 | 4 | 180 hrs | 5760 | CLUG,JLD,NH
Define evaluation criteria | 2 days | Thu 1/16/14 | Tue 1/21/14 | 5 | 72 hrs | 2970 | MG,SA,NC,MT
Identify evaluation team | 1 day | Tue 1/21/14 | Wed 1/22/14 | 6 | 27 hrs | 1080 | SA,NC,JB
Draft RFP | 6 days | Wed 1/22/14 | Wed 1/29/14 | 7 | 90 hrs | 6750 | MG,KK
Review RFP with management and lending reps. | 1.11 days | Wed 1/29/14 | Thu 1/30/14 | 8 | 36 hrs | 3510 | MG,KK,EB,LCR
Refine RFP | 1.61 days | Thu 1/30/14 | Mon 2/3/14 | 9 | 18 hrs | 1350 | MG,KK
RFP ready to release | 0 days | Mon 2/3/14 | Mon 2/3/14 | 10 | 0 hrs | 0
RFP Release | 4.89 days | Mon 2/3/14 | Mon 2/10/14 |  | 88 hrs | 6340
RFP release begins | 0 days | Mon 2/3/14 | Mon 2/3/14 | 11 | 0 hrs | 0
Identify software suppliers | 2.22 days | Mon 2/3/14 | Wed 2/5/14 | 13 | 36 hrs | 2700 | MG,KK
Determine deadline dates for responses | 2 hrs | Wed 2/5/14 | Wed 2/5/14 | 14 | 6 hrs | 280 | EB,MG,AC
Finalize RFP content | 6 hrs | Wed 2/5/14 | Thu 2/6/14 | 15 | 6 hrs | 450 | KK
Release RFP to target companies | 2 hrs | Thu 2/6/14 | Thu 2/6/14 | 16 | 4 hrs | 300 | KK,MG
Conduct RFP briefing | 1.5 days | Thu 2/6/14 | Mon 2/10/14 | 17 | 36 hrs | 2610 | MG,KK,NC,SCR
RFP release complete | 0 days | Mon 2/10/14 | Mon 2/10/14 | 18 | 0 hrs | 0
RFP Solicitation Process complete | 0 days | Mon 2/10/14 | Mon 2/10/14 | 19 | 0 hrs | 0