## WBS
*Note that the project sequence number is not the same as the excel sheet row number
Project Seq. #* | Task Name | Duration | Start After
1 | Single Family House - Architect Design
2 | Start Project Milestone | 0 days | Project start
3 | General Conditions |  | NA Calculated
4 | Finalize plans and develop estimate with owner, architect | 20 days | 2
5 | Sign contract and notice to proceed | 1 day | 4
6 | Apply for Permits |  | NA Calculated
7 | Secure foundation permit | 10 days | 5
8 | Secure framing permit | 10 days | 5
9 | Secure electrical permit | 10 days | 5
10 | Secure plumbing permit | 10 days | 5
11 | Secure HVAC permit | 10 days | 5
12 | Secure miscellaneous permits | 10 days | 5
13 | Site Work |  | NA Calculated
14 | Clear and grub lot | 1 day | 7-11
15 | Install temporary power service | 1 day | 14
16 | Install underground utilities | 1 day | 15
17 | Foundation |  | NA Calculated
18 | Excavate for foundations | 3 days
19 | Form basement walls | 13 days
20 | Place concrete for foundations & basement walls | 12 days
21 | Cure basement walls for 7 days | 7 days
22 | Strip basement wall forms | 2 days
23 | Waterproof/insulate basement walls | 2 days
24 | Perform foundation inspection | 1 day
25 | Backfill foundation | 2 days
26 | Framing
27 | Install 1st floor joists | 2 days
28 | Lay 1st floor decking | 2 days
29 | Frame 1st floor walls | 4 days
30 | Frame 1st floor corners | 1 day
31 | Install 2nd floor joists | 2 days
32 | Frame 2nd floor decking | 2 days
33 | Frame 2nd floor walls | 3 days
34 | Frame 2nd floor corners | 2 days
35 | Complete roof framing | 3 days
36 | Conduct framing inspection | 1 day
37 | Dry In
38 | Install 1st floor sheathing | 3 days
39 | Install 2nd floor sheathing | 3 days
40 | Install roof decking | 3 days
41 | Install felt, flashing and shingles | 3 days
42 | Hang 1st floor exterior doors | 1 day
43 | Install 1st floor windows | 3 days
44 | Install 2nd floor windows | 3 days
45 | Exterior Finishes
46 | Complete exterior brick | 16 days
47 | Complete exterior siding | 3 days
48 | Utility Rough-B97Ins and Complete Concrete
49 | Rough-in plumbing | 5 days
50 | Conduct rough-in plumbing inspection | 1 day
51 | Place concrete for basement floor | 11 days
52 | Rough-in electrical | 5 days
53 | Conduct rough-in electrical inspection | 1 day
54 | Rough-in HVAC | 3 days
55 | Conduct rough-in HVAC inspection | 1 day
56 | Rough-in communication - phone, cable, computer, alarm | 2 days
57 | Interior Finishes
58 | Insulation
59 | Place wall insulation - 1st floor | 1 day
60 | Place wall insulation - 2nd floor | 1 day
61 | Place ceiling insulation - 2nd floor | 1 day
62 | Conduct insulation inspection | 1 day
63 | Drywall
64 | Install drywall - 1st floor walls | 2 days
65 | Install drywall - 1st floor overhead | 2 days
66 | Install drywall 2nd floor walls | 2 days
67 | Install drywall 2nd floor overhead | 2 days
68 | Tape and float 1st floor drywall | 1 day
69 | Tape and float 2nd floor drywall | 1 day
70 | Paint and Wallpaper
71 | Texture all except entry and kitchen - 1st floor | 1 day
72 | Paint all except entry and kitchen - 1st floor | 1 day
73 | Hang wallpaper entry and kitchen - 1st floor | 1 day
74 | Texture all - 2nd floor | 1 day
75 | Paint all - 2nd floor | 1 day
76 | Paint exterior siding & trim work | 4 days
77 | Cabinets
78 | Install 1st floor - kitchen cabinets | 2 days
79 | Install 1st floor - master bath and guest cabinets | 1 day
80 | Install 2nd floor - hall bath and private bath cabinets | 1 day
81 | Install chair rails, crown moldings, trim | 2 days
82 | Finish Plumbing
83 | Complete 1st floor - kitchen plumbing | 1 day
84 | Complete 1st floor - master bath and guest plumbing | 2 days
85 | Complete 2nd floor - hall bath and private bath plumbing | 2 days
86 | Conduct finish plumbing inspection | 1 day
87 | Finish Electrical
88 | Complete 1st floor circuits to service panel | 1 day
89 | Complete 2nd floor circuits to service panel | 1 day
90 | Conduct finish electrical inspection | 1 day
91 | Complete communications wiring - phone, cable, computer, alarm | 2 days
92 | Finish HVAC
93 | Complete 1st floor - zone 1 HVAC | 1 day
94 | Complete 2nd floor - zone 2 HVAC | 1 day
95 | Conduct HVAC inspection | 1 day
96 | Carpet, Tile and Appliances
97 | Tile entry, kitchen and baths | 3 days
98 | Carpet 1st floor | 2 days
99 | Carpet 2nd floor | 2 days
100 | Install appliances | 1 day
101 | Landscaping and Grounds Work
102 | Pour concrete driveway and sidewalks | 2 days
103 | Install backyard fence | 2 days
104 | Sod and complete plantings - front yard | 2 days
105 | Sod and complete plantings - backyard | 1 day
106 | Final Acceptance
107 | Complete final inspection for certificate of occupancy | 1 day
108 | Cleanup for occupancy | 1 day
109 | Perform final walk-through inspection | 1 day
110 | Complete punch list items | 5 days
111 | End Project Milestone | 0 days