## Sheet1
Risk ID # | WBS # | Risk Category | Risk Event | Probability | Impact | Exposure Level | Response Strategy | Response Impact | Expected Value | Trigger | Priority | Responsibility
1 | 2.3 | Facilities | Unavailable | Med | High | Red | Hire Contractors | 50000 | 37500 | No Vacancy Sign | 1 | James Brown
2 | 1.1.1 | Staff | No voluteers | Low | Med | Yellow | Broaden Search | 10000 | 2000 | No one stepping up | 3 | Michael Jordan
3 | 1.2.3 | Schedule | Opportunity | High | Medium | Red | Re-Plan Project | 10000 | -5000 | Order Lead Time | 3 | Sammy Davis
Probability Estimate: | [5 empty] | Total expected value amount: |  |  | 34500
Low | 1-20% |  |  |  |  | Risk contingency (usually about 10%) |  |  | 3450 | 5-15% (depending on project)
Medium | 21-60% |  |  |  |  | Management reserve (open to judgment) |  |  | 1725 | 5-10% (depending on manager)
High | 61-99% |  |  |  |  | Total for the pool (must be in the budget) |  |  | 39675
Impact Estimate:
Low | 1-25%
Medium | 26-75%
High | 76-99%