## Sheet1
Risk ID # | WBS # | Risk Category | Risk Event | Probability | Impact | Exposure Level | Response Strategy | Response Impact | Expected Value | Trigger | Priority | Responsibility
1 | 1.2.3 | Permits | 2 | Medium | High | Red | Expedite Permit Processing | 15000 | 11250 | Permits are delayed | 1 | TBD
2 |  | Weather | 1 | Low | High | Yellow | Drain/Control Water | 40000 | 20000 | Excessive Rainfall | 2 | TBD
Probability Estimate: | [5 empty] | Total expected value amount: |  |  | 31250
Low | 1-20% |  |  |  |  | Risk contingency (usually about 10%) |  |  | 4687.5 | 5-15% (depending on project)
Medium | 21-60% |  |  |  |  | Management reserve (open to judgment) |  |  | 2500 | 5-10% (depending on manager)
High | 61-99% |  |  |  |  | Total for the pool (must be in the budget) |  |  | 38437.5
Impact Estimate:
Low | 1-25%
Medium | 26-75%
High | 76-99%