## WBS
*Note that the project sequence number is not the same as the excel sheet row number
Project Seq. #* | Task Name | Duration | Start After
1 | Single Family House - Architect Design
2 | Start Project Milestone | 0 days | Project start
3 | General Conditions |  | NA Calculated
4 | Finalize plans and develop estimate with owner, architect | 20 days | 2
5 | Sign contract and notice to proceed | 1 day | 4
6 | Apply for Permits |  | NA Calculated
7 | Secure foundation permit | 10 days | 5
8 | Secure framing permit | 10 days | 5
9 | Secure electrical permit | 10 days | 5
10 | Secure plumbing permit | 10 days | 5
11 | Secure HVAC permit | 10 days | 5
12 | Secure miscellaneous permits | 10 days | 5
13 | Site Work |  | NA Calculated
14 | Clear and grub lot | 1 day | 7-11
15 | Install temporary power service | 1 day | 14
16 | Install underground utilities | 1 day | 15
17 | Foundation |  | NA Calculated
18 | Excavate for foundations | 3 days | 14
19 | Form basement walls | 13 days | 18
20 | Place concrete for foundations & basement walls | 12 days | 19
21 | Cure basement walls for 7 days | 7 days | 20
22 | Strip basement wall forms | 2 days | 21
23 | Waterproof/insulate basement walls | 2 days | 22
24 | Perform foundation inspection | 1 day | 23
25 | Backfill foundation | 2 days | 24
26 | Framing |  | NA Calculated
27 | Install 1st floor joists | 2 days | 25
28 | Lay 1st floor decking | 2 days | 27
29 | Frame 1st floor walls | 4 days | 28
30 | Frame 1st floor corners | 1 day | 29
31 | Install 2nd floor joists | 2 days | 30
32 | Frame 2nd floor decking | 2 days | 31
33 | Frame 2nd floor walls | 3 days | 32
34 | Frame 2nd floor corners | 2 days | 33
35 | Complete roof framing | 3 days | 34
36 | Conduct framing inspection | 1 day | 35
37 | Dry In |  | NA Calculated
38 | Install 1st floor sheathing | 3 days | 36
39 | Install 2nd floor sheathing | 3 days | 36
40 | Install roof decking | 3 days | 36
41 | Install felt, flashing and shingles | 3 days | 40
42 | Hang 1st floor exterior doors | 1 day | 38
43 | Install 1st floor windows | 3 days | 38
44 | Install 2nd floor windows | 3 days | 39
45 | Exterior Finishes |  | NA Calculated
46 | Complete exterior brick | 16 days | 43
47 | Complete exterior siding | 3 days | 46
48 | Utility Rough-B97Ins and Complete Concrete |  | NA Calculated
49 | Rough-in plumbing | 5 days | 36
50 | Conduct rough-in plumbing inspection | 1 day | 49
51 | Place concrete for basement floor | 11 days | 50
52 | Rough-in electrical | 5 days | 51
53 | Conduct rough-in electrical inspection | 1 day | 52
54 | Rough-in HVAC | 3 days | 53
55 | Conduct rough-in HVAC inspection | 1 day | 54
56 | Rough-in communication - phone, cable, computer, alarm | 2 days | 55
57 | Interior Finishes |  | NA Calculated
58 | Insulation |  | NA Calculated
59 | Place wall insulation - 1st floor | 1 day | 56
60 | Place wall insulation - 2nd floor | 1 day | 59
61 | Place ceiling insulation - 2nd floor | 1 day | 60
62 | Conduct insulation inspection | 1 day | 61
63 | Drywall |  | NA Calculated
64 | Install drywall - 1st floor walls | 2 days | 62
65 | Install drywall - 1st floor overhead | 2 days | 64
66 | Install drywall 2nd floor walls | 2 days | 65
67 | Install drywall 2nd floor overhead | 2 days | 66
68 | Tape and float 1st floor drywall | 1 day | 67
69 | Tape and float 2nd floor drywall | 1 day | 68
70 | Paint and Wallpaper |  | NA Calculated
71 | Texture all except entry and kitchen - 1st floor | 1 day | 69
72 | Paint all except entry and kitchen - 1st floor | 1 day | 71
73 | Hang wallpaper entry and kitchen - 1st floor | 1 day | 72
74 | Texture all - 2nd floor | 1 day | 73
75 | Paint all - 2nd floor | 1 day | 74
76 | Paint exterior siding & trim work | 4 days | 75
77 | Cabinets |  | NA Calculated
78 | Install 1st floor - kitchen cabinets | 2 days | 76
79 | Install 1st floor - master bath and guest cabinets | 1 day | 76
80 | Install 2nd floor - hall bath and private bath cabinets | 1 day | 79
81 | Install chair rails, crown moldings, trim | 2 days | 80
82 | Finish Plumbing |  | NA Calculated
83 | Complete 1st floor - kitchen plumbing | 1 day | 79
84 | Complete 1st floor - master bath and guest plumbing | 2 days | 83
85 | Complete 2nd floor - hall bath and private bath plumbing | 2 days | 80
86 | Conduct finish plumbing inspection | 1 day | 85
87 | Finish Electrical |  | NA Calculated
88 | Complete 1st floor circuits to service panel | 1 day | 86
89 | Complete 2nd floor circuits to service panel | 1 day | 88
90 | Conduct finish electrical inspection | 1 day | 89
91 | Complete communications wiring - phone, cable, computer, alarm | 2 days | 90
92 | Finish HVAC |  | NA Calculated
93 | Complete 1st floor - zone 1 HVAC | 1 day | 91
94 | Complete 2nd floor - zone 2 HVAC | 1 day | 91
95 | Conduct HVAC inspection | 1 day | 93-94
96 | Carpet, Tile and Appliances |  | NA Calculated
97 | Tile entry, kitchen and baths | 3 days | 95
98 | Carpet 1st floor | 2 days | 97
99 | Carpet 2nd floor | 2 days | 98
100 | Install appliances | 1 day | 99
101 | Landscaping and Grounds Work |  | NA Calculated
102 | Pour concrete driveway and sidewalks | 2 days | 100
103 | Install backyard fence | 2 days | 100
104 | Sod and complete plantings - front yard | 2 days | 102
105 | Sod and complete plantings - backyard | 1 day | 102
106 | Final Acceptance |  | NA Calculated
107 | Complete final inspection for certificate of occupancy | 1 day | 105
108 | Cleanup for occupancy | 1 day | 107
109 | Perform final walk-through inspection | 1 day | 108
110 | Complete punch list items | 5 days | 109
111 | End Project Milestone | 0 days | NA Calculated