## WBS
Task Name | Duration | Days Only | Start | Finish | Predecessors | Successors | Resource Names
Single Family House - Architect Design | 162 days | 162 | Mon 1/6/14 | Tue 8/19/14
Start Project Milestone | 0 days | 0 | Mon 1/6/14 | Mon 1/6/14 |  | 4 | General contractor
General Conditions | 31 days | 31 | Mon 1/6/14 | Mon 2/17/14
Finalize plans and develop estimate with owner, architect | 20 days | 20 | Mon 1/6/14 | Fri 1/31/14 | 2 | 5 | Architect
Sign contract and notice to proceed | 1 day | 1 | Mon 2/3/14 | Mon 2/3/14 | 4 | 7,8,9,10,11,12 | Mortgage lender
Apply for Permits | 10 days | 10 | Tue 2/4/14 | Mon 2/17/14
Secure foundation permit | 10 days | 10 | Tue 2/4/14 | Mon 2/17/14 | 5 | 14 | General contractor
Secure framing permit | 10 days | 10 | Tue 2/4/14 | Mon 2/17/14 | 5 | 14 | General contractor
Secure electrical permit | 10 days | 10 | Tue 2/4/14 | Mon 2/17/14 | 5 | 14 | General contractor
Secure plumbing permit | 10 days | 10 | Tue 2/4/14 | Mon 2/17/14 | 5 | 14 | General contractor
Secure HVAC permit | 10 days | 10 | Tue 2/4/14 | Mon 2/17/14 | 5 | 14 | General contractor
Secure miscellaneous permits | 10 days | 10 | Tue 2/4/14 | Mon 2/17/14 | 5 | 14 | General contractor
Site Work | 3 days | 3 | Tue 2/18/14 | Thu 2/20/14
Clear and grub lot | 1 day | 1 | Tue 2/18/14 | Tue 2/18/14 | 7,8,9,10,12,11 | 15 | Site excavation contractor
Install temporary power service | 1 day | 1 | Wed 2/19/14 | Wed 2/19/14 | 14 | 16 | Electric company
Install underground utilities | 1 day | 1 | Thu 2/20/14 | Thu 2/20/14 | 15 | 18 | Site excavation contractor
Foundation | 42 days | 42 | Fri 2/21/14 | Mon 4/21/14
Excavate for foundations | 3 days | 3 | Fri 2/21/14 | Tue 2/25/14 | 16 | 19,24
Form basement walls | 13 days | 13 | Wed 2/26/14 | Fri 3/14/14 | 18 | 20 | Site excavation contractor
Place concrete for foundations & basement walls | 12 days | 12 | Mon 3/17/14 | Tue 4/1/14 | 19 | 21 | Concrete contractor
Cure basement walls for 7 days | 7 days | 7 | Wed 4/2/14 | Thu 4/10/14 | 20 | 22 | Concrete contractor
Strip basement wall forms | 2 days | 2 | Fri 4/11/14 | Mon 4/14/14 | 21 | 23 | Concrete contractor
Waterproof/insulate basement walls | 2 days | 2 | Tue 4/15/14 | Wed 4/16/14 | 22 | 24 | Insulation contractor
Perform foundation inspection | 1 day | 1 | Thu 4/17/14 | Thu 4/17/14 | 23,18 | 25 | Inspector
Backfill foundation | 2 days | 2 | Fri 4/18/14 | Mon 4/21/14 | 24 | 27 | Site excavation contractor
Framing | 22 days | 22 | Tue 4/22/14 | Wed 5/21/14
Install 1st floor joists | 2 days | 2 | Tue 4/22/14 | Wed 4/23/14 | 25 | 28 | Framing contractor
Lay 1st floor decking | 2 days | 2 | Thu 4/24/14 | Fri 4/25/14 | 27 | 29 | Framing contractor
Frame 1st floor walls | 4 days | 4 | Mon 4/28/14 | Thu 5/1/14 | 28 | 30 | Framing contractor
Frame 1st floor corners | 1 day | 1 | Fri 5/2/14 | Fri 5/2/14 | 29 | 31 | Framing contractor
Install 2nd floor joists | 2 days | 2 | Mon 5/5/14 | Tue 5/6/14 | 30 | 32 | Framing contractor
Frame 2nd floor decking | 2 days | 2 | Wed 5/7/14 | Thu 5/8/14 | 31 | 33 | Framing contractor
Frame 2nd floor walls | 3 days | 3 | Fri 5/9/14 | Tue 5/13/14 | 32 | 34 | Framing contractor
Frame 2nd floor corners | 2 days | 2 | Wed 5/14/14 | Thu 5/15/14 | 33 | 35 | Framing contractor
Complete roof framing | 3 days | 3 | Fri 5/16/14 | Tue 5/20/14 | 34 | 36,40 | Framing contractor
Conduct framing inspection | 1 day | 1 | Wed 5/21/14 | Wed 5/21/14 | 35 | 38 | Inspector
Dry In | 22 days | 22 | Wed 5/21/14 | Thu 6/19/14
Install 1st floor sheathing | 3 days | 3 | Thu 5/22/14 | Mon 5/26/14 | 36 | 39,59 | Framing contractor
Install 2nd floor sheathing | 3 days | 3 | Tue 5/27/14 | Thu 5/29/14 | 38 | 49,52,59 | Framing contractor
Install roof decking | 3 days | 3 | Wed 5/21/14 | Fri 5/23/14 | 35 | 49,52,56 | Framing contractor
Install felt, flashing and shingles | 3 days | 3 | Fri 6/6/14 | Tue 6/10/14 | 49 | 42 | Roofing contractor
Hang 1st floor exterior doors | 1 day | 1 | Wed 6/11/14 | Wed 6/11/14 | 41 | 43 | Finish carpentry contractor
Install 1st floor windows | 3 days | 3 | Thu 6/12/14 | Mon 6/16/14 | 42 | 44 | Finish carpentry contractor
Install 2nd floor windows | 3 days | 3 | Tue 6/17/14 | Thu 6/19/14 | 43 | 46,59 | Finish carpentry contractor
Exterior Finishes | 19 days | 19 | Fri 6/20/14 | Wed 7/16/14
Complete exterior brick | 16 days | 16 | Fri 6/20/14 | Fri 7/11/14 | 44 | 47 | Masonry contractor
Complete exterior siding | 3 days | 3 | Mon 7/14/14 | Wed 7/16/14 | 46 | 76 | Siding conractor
Utility Rough-B97Ins and Complete Concrete | 21 days | 21 | Mon 5/26/14 | Mon 6/23/14
Rough-in plumbing | 5 days | 5 | Fri 5/30/14 | Thu 6/5/14 | 40,39 | 41,50 | Plumbing contractor
Conduct rough-in plumbing inspection | 1 day | 1 | Fri 6/6/14 | Fri 6/6/14 | 49 | 51,83 | Inspector
Place concrete for basement floor | 11 days | 11 | Mon 6/9/14 | Mon 6/23/14 | 50 | 107 | Concrete contractor
Rough-in electrical | 5 days | 5 | Fri 5/30/14 | Thu 6/5/14 | 40,39 | 53,59 | Electric contractor
Conduct rough-in electrical inspection | 1 day | 1 | Fri 6/6/14 | Fri 6/6/14 | 52 | 54,88 | Inspector
Rough-in HVAC | 3 days | 3 | Mon 6/9/14 | Wed 6/11/14 | 53 | 55,59 | Heating and AC contractor
Conduct rough-in HVAC inspection | 1 day | 1 | Thu 6/12/14 | Thu 6/12/14 | 54 | 93 | Inspector
Rough-in communication - phone, cable, computer, alarm | 2 days | 2 | Mon 5/26/14 | Tue 5/27/14 | 40 | 59 | Electric contractor
Interior Finishes | 30 days | 30 | Fri 6/20/14 | Thu 7/31/14
Insulation | 11 days | 11 | Fri 6/20/14 | Fri 7/4/14
Place wall insulation - 1st floor | 1 day | 1 | Fri 6/20/14 | Fri 6/20/14 | 38,44,56,54,52,39 | 60,64 | Insulation contractor
Place wall insulation - 2nd floor | 1 day | 1 | Mon 6/23/14 | Mon 6/23/14 | 59 | 61,66 | Insulation contractor
Place ceiling insulation - 2nd floor | 1 day | 1 | Thu 7/3/14 | Thu 7/3/14 | 67,60 | 62 | Insulation contractor
Conduct insulation inspection | 1 day | 1 | Fri 7/4/14 | Fri 7/4/14 | 61 | 107 | Inspector
Drywall | 9 days | 9 | Mon 6/23/14 | Thu 7/3/14
Install drywall - 1st floor walls | 2 days | 2 | Mon 6/23/14 | Tue 6/24/14 | 59 | 65 | Drywall contractor
Install drywall - 1st floor overhead | 2 days | 2 | Wed 6/25/14 | Thu 6/26/14 | 64 | 66,68 | Drywall contractor
Install drywall 2nd floor walls | 2 days | 2 | Fri 6/27/14 | Mon 6/30/14 | 65,60 | 67 | Drywall contractor
Install drywall 2nd floor overhead | 2 days | 2 | Tue 7/1/14 | Wed 7/2/14 | 66 | 61,69 | Drywall contractor
Tape and float 1st floor drywall | 1 day | 1 | Fri 6/27/14 | Fri 6/27/14 | 65 | 69,71 | Drywall contractor
Tape and float 2nd floor drywall | 1 day | 1 | Thu 7/3/14 | Thu 7/3/14 | 67,68 |  | Drywall contractor
Paint and Wallpaper | 17 days | 17 | Mon 6/30/14 | Tue 7/22/14
Texture all except entry and kitchen - 1st floor | 1 day | 1 | Mon 6/30/14 | Mon 6/30/14 | 68 | 72,74 | Painting contractor
Paint all except entry and kitchen - 1st floor | 1 day | 1 | Tue 7/1/14 | Tue 7/1/14 | 71 | 73 | Painting contractor
Hang wallpaper entry and kitchen - 1st floor | 1 day | 1 | Wed 7/2/14 | Wed 7/2/14 | 72 | 78 | Painting contractor
Texture all - 2nd floor | 1 day | 1 | Tue 7/1/14 | Tue 7/1/14 | 71 | 75 | Painting contractor
Paint all - 2nd floor | 1 day | 1 | Wed 7/2/14 | Wed 7/2/14 | 74 |  | Painting contractor
Paint exterior siding & trim work | 4 days | 4 | Thu 7/17/14 | Tue 7/22/14 | 47 | 102 | Painting contractor
Cabinets | 6 days | 6 | Thu 7/3/14 | Thu 7/10/14
Install 1st floor - kitchen cabinets | 2 days | 2 | Thu 7/3/14 | Fri 7/4/14 | 73 | 79,83 | Finish carpentry contractor
Install 1st floor - master bath and guest cabinets | 1 day | 1 | Mon 7/7/14 | Mon 7/7/14 | 78 | 80,84 | Finish carpentry contractor
Install 2nd floor - hall bath and private bath cabinets | 1 day | 1 | Tue 7/8/14 | Tue 7/8/14 | 79 | 81,85 | Finish carpentry contractor
Install chair rails, crown moldings, trim | 2 days | 2 | Wed 7/9/14 | Thu 7/10/14 | 80 | 107 | Finish carpentry contractor
Finish Plumbing | 6 days | 6 | Mon 7/7/14 | Mon 7/14/14
Complete 1st floor - kitchen plumbing | 1 day | 1 | Mon 7/7/14 | Mon 7/7/14 | 78,50 | 84 | Plumbing contractor
Complete 1st floor - master bath and guest plumbing | 2 days | 2 | Tue 7/8/14 | Wed 7/9/14 | 83,79 | 85 | Plumbing contractor
Complete 2nd floor - hall bath and private bath plumbing | 2 days | 2 | Thu 7/10/14 | Fri 7/11/14 | 84,80 | 86,88 | Plumbing contractor
Conduct finish plumbing inspection | 1 day | 1 | Mon 7/14/14 | Mon 7/14/14 | 85 | 91107 | Inspector
Finish Electrical | 3 days | 3 | Mon 7/14/14 | Wed 7/16/14
Complete 1st floor circuits to service panel | 1 day | 1 | Mon 7/14/14 | Mon 7/14/14 | 85,53 | 89 | Electric contractor
Complete 2nd floor circuits to service panel | 1 day | 1 | Tue 7/15/14 | Tue 7/15/14 | 88 | 90 | Electric company
Conduct finish electrical inspection | 1 day | 1 | Wed 7/16/14 | Wed 7/16/14 | 89 | 97107 | Inspector
Complete communications wiring - phone, cable, computer, alarm | 2 days | 2 | Tue 7/15/14 | Wed 7/16/14 | 86 | 93 | Electric contractor
Finish HVAC | 3 days | 3 | Thu 7/17/14 | Mon 7/21/14
Complete 1st floor - zone 1 HVAC | 1 day | 1 | Thu 7/17/14 | Thu 7/17/14 | 91,55 | 94 | Heating and AC contractor
Complete 2nd floor - zone 2 HVAC | 1 day | 1 | Fri 7/18/14 | Fri 7/18/14 | 93 | 95 | Heating and AC contractor
Conduct HVAC inspection | 1 day | 1 | Mon 7/21/14 | Mon 7/21/14 | 94 | 97107 | Inspector
Carpet, Tile and Appliances | 8 days | 8 | Tue 7/22/14 | Thu 7/31/14
Tile entry, kitchen and baths | 3 days | 3 | Tue 7/22/14 | Thu 7/24/14 | 90,95 | 98 | Masonry contractor
Carpet 1st floor | 2 days | 2 | Fri 7/25/14 | Mon 7/28/14 | 97 | 99 | Flooring contractor
Carpet 2nd floor | 2 days | 2 | Tue 7/29/14 | Wed 7/30/14 | 98 | 100 | Flooring contractor
Install appliances | 1 day | 1 | Thu 7/31/14 | Thu 7/31/14 | 99 | 103108 | Appliance contractor
Landscaping and Grounds Work | 12 days | 12 | Wed 7/23/14 | Thu 8/7/14
Pour concrete driveway and sidewalks | 2 days | 2 | Wed 7/23/14 | Thu 7/24/14 | 76 | 103 | Concrete contractor
Install backyard fence | 2 days | 2 | Fri 8/1/14 | Mon 8/4/14 | 100102 | 104 | Fencing contractor
Sod and complete plantings - front yard | 2 days | 2 | Tue 8/5/14 | Wed 8/6/14 | 103 | 105 | Landscape contractor
Sod and complete plantings - backyard | 1 day | 1 | Thu 8/7/14 | Thu 8/7/14 | 104 | 107 | Landscape contractor
Final Acceptance | 8 days | 8 | Fri 8/8/14 | Tue 8/19/14
Complete final inspection for certificate of occupancy | 1 day | 1 | Fri 8/8/14 | Fri 8/8/14 | 105,95,90,86,62,81,51 | 108 | Inspector
Cleanup for occupancy | 1 day | 1 | Mon 8/11/14 | Mon 8/11/14 | 100107 | 109 | Maid service
Perform final walk-through inspection | 1 day | 1 | Tue 8/12/14 | Tue 8/12/14 | 108 | 110 | Owner
Complete punch list items | 5 days | 5 | Wed 8/13/14 | Tue 8/19/14 | 109 | 111 | General contractor
End Project Milestone | 0 days | 0 | 2014-08-19 | Tue 8/19/14 | 110

## Labor Resources
Resource Name | Rate | Estimated hours | Estimated start | Estimated End
Appliance contractor | 0 | 8 | Thu 7/31/14 | Thu 7/31/14
Architect | 60 | 160 | Mon 1/6/14 | Fri 1/31/14
Concrete contractor | 65 | 272 | Mon 3/17/14 | Mon 4/14/14
Drywall contractor | 58 | 80 | Mon 6/23/14 | Thu 7/3/14
Electric company | 0 | 16 | Wed 2/19/14 | Wed 2/19/14
Electric contractor | 45 | 80 | Fri 5/30/14 | Thu 6/5/14
Fencing contractor | 55 | 16 | Fri 8/1/14 | Mon 8/4/14
Finish carpentry contractor | 50 | 104 | Wed 6/11/14 | Thu 6/19/14
Flooring contractor | 76 | 32 | Fri 7/25/14 | Wed 7/30/14
Framing contractor | 40 | 240 | Tue 4/22/14 | Tue 5/20/14
General contractor | 70 | 200 | Mon 1/6/14 | Tue 8/19/14
Heating and AC contractor | 80 | 40 | Mon 6/9/14 | Fri 7/18/14
Inspector | 0 | 80 | Thu 4/17/14 | Fri 8/8/14
Insulation contractor | 90 | 40 | Tue 4/15/14 | Thu 7/3/14
Landscape contractor | 40 | 24 | Tue 8/5/14 | Thu 8/7/14
Maid service | 50 | 8 | Mon 8/11/14 | Mon 8/11/14
Masonry contractor | 80 | 152 | Fri 6/20/14 | Thu 7/24/14
Mortgage lender | 0 | 0 | Mon 2/3/14 | Mon 2/3/14
Owner | 0 | 8 | Tue 8/12/14 | Tue 8/12/14
Painting contractor | 47 | 72 | Mon 6/30/14 | Tue 7/22/14
Plumbing contractor | 45 | 80 | Fri 5/30/14 | Fri 7/11/14
Roofing contractor | 50 | 24 | Fri 6/6/14 | Tue 6/10/14
Siding conractor | 42 | 24 | Mon 7/14/14 | Wed 7/16/14
Site excavation contractor | 150 | 16 | Tue 2/18/14 | Mon 4/21/14